## Dashboard
Project Name | Personal Netbanking System
Reference Document | FRS
Created By | Nehal Nandane
Creation Date | 2023-11-23
Approval Date | DD-MM-YYYY
Abstract | This project is aimed at testing an Online Netbanking for customer. The system is an online application that can be accessed throughout the organization and outside as well with proper outside as well with proper login provided. For testing purpose project divided into several modules.
Test Scenario | Pass | Fail | Blocked | Not Tested | Total
(TS_001) Login Functionality | 14 | 1 | 1 | 0 | 16
(TS_002) Logout | 7 | 1 | 0 | 0 | 8
(TS_003) Forgot Passsword | 8 | 1 | 0 | 0 | 9
(TS_004) Accounts | 6 | 1 | 1 | 0 | 8
(TS_005) Fund Transfer | 15 | 2 | 1 | 1 | 19
(TS_006) Cards | 11 | 0 | 0 | 0 | 11
(TS_007) Loans | 4 | 0 | 0 | 0 | 4
(TS_008) Offers | 8 | 1 | 0 | 0 | 9
(TS_009) Investment | 3 | 0 | 0 | 0 | 3
Total | 76 | 7 | 3 | 1 | 87

## Test Scenarios
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
(TS_001) Login Functionality | FRS | Validate the working of Login functionality | P0 | 14
(TS_002) Logout | FRS | Validate the working of Logout functionality | P0 | 08
(TS_003) Forgot Passsword | FRS | Validate the working of Forgot Password functionality | P2 | 09
(TS_004) Accounts | FRS | Validate the working of Account functionality | P1 | 08
(TS_005) Fund Transfer | FRS | Validate the working of Fund Transfer functionality | P1 | 19
(TS_006) Cards | FRS | Validate the Cards functionality | P1 | 11
(TS_007) Loans | FRS | Validate the Loans functionality | P1 | 04
(TS_008) Offers | FRS | Validate the working of 'Offer' functionality | P4 | 09
(TS_009) Investment | FRS | Validate the Investment functionality | P2 | 03

## Login Functionality
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_LF_001 | (TS_001) Login Functionality | Verify if the bank website login page does not appear forged. | 1. Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on the 'Customer ID/ User ID' textbox 2. Enter valid Customer ID and Click on the "Continue" option 3. Enter valid Password/ IPIN into the 'Password' field - <Refer Test Data> 4. Select all the required checkboxes 5. Click on the 'Login' button. | https://netbanking.hdfcbank.com/netbanking/ | 1. The bank website login page does not appear forged. | 1. The bank website login page does not appear forged. | P1 | PASS
TC_LF_001 | (TS_001) Login Functionality | Verify if the bank login page has a username and password. | 1. Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on the 'Customer ID/ User ID' textbox 2. Enter valid Customer ID and Click on the "Continue" option 3. Enter valid Password/ IPIN into the 'Password' field - <Refer Test Data> 4. Select all the required checkboxes 5. Click on the 'Login' button. | https://netbanking.hdfcbank.com/netbanking/ | Verify if the bank login page has a custmer ID | Verify if the bank login page has a custmer ID | P1 | PASS
TC_LF_001 | (TS_001) Login Functionality | Validate logging into the website using valid credentials | 1. Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser 2. Login credentials for an existing account are required | 1. Click on the 'Customer ID/ User ID' textbox 2. Enter valid Customer ID and Click on the "Continue" option 3. Enter valid Password/ IPIN into the 'Password' field - <Refer Test Data> 4. Select all the required checkboxes 5. Click on the 'Login' button. | Customer ID - 128654925 Password - 12345 | 1.User should be navigated to Login page 2.User should get logged in and taken to the 'Account' page | 1.User should be navigated to Login page 2.User should get logged in and taken to the 'Account' page | P1 | PASS
TC_LF_002 | (TS_001) Login Functionality | Validate logging into the Website using invalid credentials (i.e. Invalid Customer ID and Invalid Password) | Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on the 'Customer ID/ User ID' textbox 2. Enter invalid Customer ID and Click on the "Continue" option 3. Enter invalid Password/ IPIN into the 'Password' field - <Refer Test Data> 4. Select all the required checkboxes 5. Click on the 'Login' button. | Customer ID - 036 Password - xyzabc123 | 1. Warning message with the text "Customer ID length should be min of 4 characters." | Warning message with the text "Customer ID length should be min of 4 characters." | P1 | PASS
TC_LF_003 | (TS_001) Login Functionality | Validate logging into the Website using invalid Customer ID and valid Password) | Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on the 'Customer ID/ User ID' textbox 2. Enter valid Customer ID and Click on the "Continue" option 3. Enter invalid Password/ IPIN into the 'Password' field - <Refer Test Data> 4. Select all the required checkboxes 5. Click on the 'Login' button. | Customer ID - 1225vjk Password - 12345 | 1. Tampered Data Found in Request | Tampered Data Found in Request | P1 | PASS
TC_LF_004 | (TS_001) Login Functionality | Validate logging into the Website using valid Customer ID and invalid Password) | Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on the 'Customer ID/ User ID' textbox 2. Enter valid Customer ID and Click on the "Continue" option 3. Enter invalid Password/ IPIN into the 'Password' field - <Refer Test Data> 4. Select all the required checkboxes 5. Click on the 'Login' button. | Customer ID - 128654925 Password - 123ghcvhju | 1. Tampered Data Found in Request | Tampered Data Found in Request | P1 | PASS
TC_LF_005 | (TS_001) Login Functionality | Validate logging into the Website without providing any credentials | Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on the 'Customer ID/ User ID' textbox 2. Enter valid Customer ID and Click on the "Continue" option 3. Enter invalid Password/ IPIN into the 'Password' field - <Refer Test Data> 4. Select all the required checkboxes 5. Click on the 'Login' button. | Not Applicable | Customer ID cannot be left blank. | Customer ID cannot be left blank. | P1 | PASS
TC_LF_006 | (TS_001) Login Functionality | Validate 'Forgotten Password' link is available in the Login page and is working | Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on the 'Customer ID/ User ID' textbox 2. Enter valid Customer ID and Click on the "Continue" option 3. Click on 'Forgot Password/ IPIN' link (ER-2) | Customer ID - 128654925 Password - NA | 1. User should be taken to 'Login' page and 'Forgotten Password' link should be displayed in the page 2. User should be taken to 'Forgotten Password' page | 1. User is taken to 'Login' page and 'Forgotten Password' link should be displayed in the page 2. User is taken to 'Forgotten Password' page | P3 | PASS
TC_LF_007 | (TS_001) Login Functionality | Validate logging into the Website using Keyboard keys (Tab and Enter) | Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on the 'Customer ID/ User ID' textbox 2. Enter a valid Customer ID and Click on the "Continue" option 4. Select Use virtual keyboard for password Checkbox. 5. Press Tab keyboard key with valid password the control comes 'Login' button and press 'Enter' key to submit (ER-1) | Not Applicable | 1. User should be able to log into the Website | User is able to log into the Website | P3 | PASS
TC_LF_008 | (TS_001) Login Functionality | Validate logging into the Website using inactive credentials | Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on the 'Customer ID/ User ID' textbox 2. Enter inactive Customer ID and Click on the "Continue" option 3. Enter valid Password/ IPIN into the 'Password' field - <Refer Test Data> 4. Select all the required checkboxes 5. Click on the 'Login' button. | Test Data for this is pending | 1. User should not be able to login | 1. User should not be able to login | P2 | Blocked | Unable to test as we don't have the credentails of an inactive account for testing it
TC_LF_009 | (TS_001) Login Functionality | Validate the number of unsucessful login attemps | Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on the 'Customer ID/ User ID' textbox 2. Enter valid Customer ID and Click on the "Continue" option 3. Enter invalid Password/ IPIN into the 'Password' field - <Refer Test Data> 4. Select all the required checkboxes 5. Click on the 'Login' button. | Customer ID - 128654925 Password - 12345wjb | 1. Warning message with the text ' Warning: Your account has exceeded allowed number of login attempts. Please try again in x hour.' | Warning message with the text ' Warning: Your account has exceeded allowed number of login attempts. Please try again in x hour.' | P2 | PASS
TC_LF_010 | (TS_001) Login Functionality | Validate Logging into the Website after changing the password | Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Enter valid Customer ID field - <Refer Test Data> 2. Enter valid password into the 'Password' field - <Refer Test Data> 3. Click on 'Login' button 4. Click on 'Change your password' link 5. Enter new password into the 'Password' and 'Password Confirm' fields 6. Click on 'Continue' button 7. Click on 'My Account' Dropmenu and select 'Logout' option 8. Repeat steps 1 to 5 (ER-1) 9. Enter new credentials given in Step 7 and click on 'Login' button (ER-2) | Customer ID - 128654925 Password - 12345 | 1. User should not be allowed to login 2. User should be able to login | 1. User is not allowed to login with old credentials 2. User is able to login with new credentials | P2 | PASS
TC_LF_011 | (TS_001) Login Functionality | Validate timeout of the Login Session | Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on the 'Customer ID/ User ID' textbox 2. Enter valid Customer ID and Click on the "Continue" option 3. Enter valid Password/ IPIN into the 'Password' field - <Refer Test Data> 4. Select all the required checkboxes 5. Click on the 'Login' button. 6. Stay on same page without tapping on anything for x minute. | Customer ID - 128654925 Password - 12345 | 1. User should get automatically logged out with a proper message stating your session got expired. | 1. User is getting automatically logged out with a proper message stating your session got expired. | P3 | FAIL | OPENCART-BUG-10
TC_LF_012 | (TS_001) Login Functionality | Validate the Breakcrumb, Page Heading, Page Title and Page URL of Login page | Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on Customer ID check box 2. Click on 'Login' option (ER-1) | Not Applicable | 1. Proper Breadcrumb, Page Heading, Page URL and Page Title should be displayed | 1. Proper Breadcrumb, Page Heading, Page URL and Page Title is displayed | P3 | PASS
TC_LF_013 | (TS_001) Login Functionality | Validate the UI of the Login page | Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on Customer ID check box 2. Click on 'Login' option (ER-1) | Not Applicable | 1. Login page UI should adhere to the UI checklist | 1. Login page UI is according to the UI checklist | P3 | PASS
TC_LF_014 | (TS_001) Login Functionality | Validate the Login page functionality in all the supported environments | Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Click on Customer ID check box 2. Click on 'Login' option (ER-1) | Not Applicable | 1. Login functionality should work correctly in all the supported environments | 1. Login functionality is working correctly in all the supported environments | P3 | PASS

## Logout
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_LG_001 | (TS_002) Logout Functionality | Validate Logging out by selecting Logout option from top navigation bar | 1. Open the Website URL 2. User is logged in | 1. Click on top navigation bar 2. Select 'Logout' option (Verify ER-1) 3. Click on 'Continue' button (Verify ER-2) | Not Applicable | 1. User should be taken to the 'Account Logout' page and User should see Login option. 2. User should be taken to the Home page | 1. User is taken to the 'Account Logout' page and User should see Login option. 2. User is taken to the Home page | P1 | PASS
TC_LG_002 | (TS_002) Logout Functionality | Validate Logging out by selecting Logout option from top navigation bar | 1. Open the Website URL 2. User is logged in and is on 'Account' page | 1. Click on 'Logout' option from top navigation bar 2. Click on 'Continue' button (Verify ER-2) | Not Applicable | 1. User should be taken to the 'Account Logout' page and User should see Login option. 2. User should be taken to the Home page | 1. User is taken to the 'Account Logout' page and the User should see Login option. 2. User is taken to the Home page | P3 | PASS
TC_LG_003 | (TS_002) Logout Functionality | Validate the Website session status, after logging and closing the Browser without logging out | 1. Open the Website URL 2. User is logged in | 1. Close the Browser without Logging out 2. Open the Browser and navigate the Website (Verify ER-1) | Not Applicable | 1. Website should get logged out. | 1. Website is logged out. | P3 | PASS
TC_LG_004 | (TS_002) Logout Functionality | Validate logging out and browsing back | 1. Open the Website URL 2. User is logged in | 1. Click on top navigation bar. 2. Select 'Logout' option 3. Click on Browser back button (Verify ER-1) | Not Applicable | 1. User should not get logged in | 1. User is getting logged in | P1 | FAIL | OPEN Banking-BUG-1 (User is able to get logged in after browsing back)
TC_LG_005 | (TS_002) Logout Functionality | Validate logging out and loggin in immediately after logout | 1. Open the Website URL 2. User is logged in | 1. Click on 'top navigation bar 2. Select 'Logout' option 3. Login immediately again with same or different account (Verify ER-1) | Not Applicable | 1. Same Account or Differnet Account should get loggedin | 1. Same Account or Differnet Account is get loggedin | P3 | PASS
TC_LG_006 | (TS_002) Logout Functionality | Validate 'Account Logout' page | 1. Open the Website URL 2. User is logged in | 1. Click on top navigation bar 2. Select 'Logout' option 3. User get successfully logged out. | Not Applicable | 1. Proper Page Heading, Page Title, Page URL and Breadcrumb are displayed for 'Account Logout' page | 1. Proper Page Heading, Page Title, Page URL and Breadcrumb is displayed for 'Account Logout' page | P3 | PASS
TC_LG_007 | (TS_002) Logout Functionality | Validate the UI of the Logout option and the 'Account Logout' page | 1. Open the Website URL 2. User is logged in | 1. Click on 'top navigation bar 2. Select 'Logout' option (Verify ER-1) | Not Applicable | 1. Proper UI adhering to the UI checklist should be displayed for Logout option | 1. Proper UI adhering to the UI checklist is displayed for Logout option | P3 | PASS
TC_LG_008 | (TS_002) Logout Functionality | Validate the Logout functionality in all the supported environments | 1. Open the Website URL 2. User is logged in | 1. Click on top navigation bar 2. Select 'Logout' option (Verify ER-1) | Not Applicable | 1. Logout functionality should work correctly in all the supported environments | 1. Logout functionality is working correctly in all the supported environments | P3 | PASS

## Forgot Passsword
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_FP_001 | (TS_003) Forgot Passsword | Validate User is able to reset the password | 1. Open the Website URL and navigate to Login Page 2. An existing Account is required | 1. Click on 'Forgotten Password' link from Login page (Validate ER-1) 2. Enter the customer ID of an existing account for which you have forgot the password 3. Click on 'Continue' button (Validate ER-2) 4. Check the registered email address for OTP 5. Check the registered mobile number for OTP 6. Enter new password into the 'Password' and 'Confirm' fields 7. Click on 'Continue' button (Validate ER-5) 8. Enter Customer ID 9. Click on 'Login' button (Validate ER-6) | Not Applicable | 1. User should be taken to 'Forgotten Password' page 2. Navigate to Password reste page 3. Validate that an OTP is received regarding resseting of the password to the registered email address. 4. Validate that an OTP is received regarding resseting of the password to the registered mobile number 4. User should be taken 'Reset your Password' page 5. Success message with text - 'Success: Your password has been successfully updated.' should be displayed in green color and User should be navigated to 'Login' page 6. User should be able to login with the new password | Password got reset and customer able to login, | P1 | PASS
TC_FP_002 | (TS_003) Forgot Passsword | Validate an email is sent with the proper details on resetting the password | 1. Open the Website URL and navigate to Login Page 2. An existing Account is required | 1. Click on 'Forgotten Password' link from Login page 2. Enter the customer ID of an existing account for which you have forgotten the password 3. Click on 'Continue' button 4. Check the registered email address for which the password got reset (Validate ER-1 and ER-2) | Not Applicable | 1. An email should be recevied by the registered email address with the details of resetting the password. 2. Email should contain proper Subject, Body, from address and the link for resetting the password | 1. An email recevied by the registered email address with the details of resetting the password. 2. Email contain proper Subject, Body, from address and the link for resetting the password | P2 | PASS
TC_FP_003 | (TS_003) Forgot Passsword | Validate logging into the Website with the old password after resetting it | 1. An existing Account is required and we have reset the password 2. Open the Website URL and navigate to Login Page | 1. Enter registered Customer ID 2. Enter old password into the 'Password' field 3. Click on 'Login' button (Validate ER-1) | Not Applicable | 1. User should not be able to login with old password | 1. User is able to login with old password | P2 | FAIL | OPEN Banking-BUG-2 (User is able to get logged in with old as well as new password)
TC_FP_004 | (TS_003) Forgot Passsword | Validate resetting the password for a non-registered account | 1. Open the Website URL and navigate to Login Page | 1.Click on 'Forgotten Password' link from Login page 2. Enter an Customer ID for which the Account doesn't exist in the Website 3. Click on 'Continue' button | Customer ID - 036 Password - xyzabc123 | 1. Warning message with the text "Customer ID length should be min of 4 characters." | 1. Warning message with the text "Customer ID length should be min of 4 characters." | P2 | PASS
TC_FP_005 | (TS_003) Forgot Passsword | Validate the User has given the same password into the 'Password' and 'Confirm' fields of the 'Reset your Password' page | 1. Open the Website URL and navigate to Login Page 2. An existing Account is required | 1. Click on 'Forgotten Password' link from Login page 2. Enter the Customer ID of an existing account for which you have forgot the password 3. Click on 'Continue' button 4. Check the registered email address and mobile number for OTP. 5. Click on the link for resseting the password from the received email body 6. Enter a password into the 'Password' field 7. Enter a different password into the 'Confirm' fields 8. Click on 'Continue' button (Validate ER-1) | Not Applicable | User is not able to reset the paasword | 1. User is not able to reset the paasword New password is not matching. | P2 | PASS
TC_FP_006 | (TS_003) Forgot Passsword | Validate the placeholders are displayed in the 'Password' and 'Confirm' fields of 'Reset your password' page | 1. An existing Account is required, we have reset the password for this account and a reset password email is sent to the registered email address | 1. Click on the reset password link available in the email 2. Check whether the 'Password' and 'Confirm' fields in the 'Reset your Password' page (Validate ER-1) | Not Applicable | 1. Proper placeholder texts are displayed inside the 'Password' and 'Confirm' fields of the 'Reset your Password' page | 1. Proper placeholder texts are displayed inside the 'Password' and 'Confirm' fields of the 'Reset your Password' page | P3 | PASS
TC_FP_007 | (TS_003) Forgot Passsword | Validate resetting the password without giving the new password in the 'Password' and 'Confirm' fields of 'Reset your Password' page | 1. An existing Account is required, we have reset the password for this account and navigates to a reset password email | 1. Click on the reset password link available 2. Don't enter any password into the 'Password' and 'Confirm' fields of the 'Reset your Password' page 3. Click on 'Continue' button (Validate ER-1) | Not Applicable | 1. Field level warning message with text - 'Password must be between 4 and 20 characters!' should be displayed for 'Password' field | 1. Field level warning message with text - 'Password must be between 4 and 20 characters!' should be displayed for 'Password' field | P3 | PASS
TC_FP_008 | (TS_003) Forgot Passsword | Validate clicking 'Back' button on the 'Reset your Password' page | 1. An existing Account is required, we have reset the password for this account and a reset password email is sent to the registered email address | 1. Click on the reset password link available in the email 2. Click on 'Back' button on the 'Reset your Password' page (Validate ER-1) | Not Applicable | 1. User should be navigated to 'Login' page | 1. User should be navigated to 'Login' page | P3 | PASS
TC_FP_009 | (TS_003) Forgot Passsword | Validate the Password Reset functionality in all the supported environments | 1. Open the Website URL and navigate to Login Page | 1. Click on 'Forgotten Password' link from Login page | Not Applicable | 1. Reset Password functionality should work correctly in all the supported environments | 1. Reset Password functionality should work correctly in all the supported environments | P2 | PASS

## Accounts
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_AC_001 | (TS_004) Accounts | Verify if the user is redirected to the dashboard after passing all authentication processes. | 1. Open the Website URL 2. User is logged in | 1. Click on the 'Customer ID/ User ID' textbox 2. Enter a valid Customer ID and Click on the "Continue" option 3. Enter valid Password/ IPIN into the 'Password' field - <Refer Test Data> 4. Select all the required checkboxes 5. Click on the 'Login' button. 6. Verify the user is redirected to the dashboard. | Customer ID - 128654925 Password - 12345 | 1. Verify if the bank login page has a customer ID 2. The user is redirected to the dashboard. | 1. Verify if the bank login page has a customer ID 2. The user is redirected to the dashboard. | P1 | PASS
TC_AC_002 | (TS_004) Accounts | Verify that the correct account details is getting displayed on the accounts page. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Accounts from the navigation bar. 3. Tap on Account Summary from the left navigation bar. 4. Check the available balance for the account on Total Available Balance. 5. Tap on the forward arrow beside Total Available Balance. 6. Verify that the Correct account number with the correct details is getting displayed. | Customer ID - 128654925 Password - 12345 | 1. User is able to log in successfully. 2. The User should be taken to the 'Account page and the User should see the correct account details. | 1. User is able to log in successfully. 2. The User should be taken to the 'Account page and the User should see the correct account details. | P1 | PASS
TC_AC_003 | (TS_004) Accounts | Verify that the user can view their account balance and transaction history. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Accounts from the navigation bar. 3. Tap on Account Summary from the left navigation bar. 4. Check the available balance for the account on Total Available Balance. 5. Tap on the forward arrow beside Total Available Balance. 6. Verify that the Correct account number with the correct details is getting displayed. 7. Tap on "View" from right corner. 8. Verify the correct transaction history. | Customer ID - 128654925 Password - 12345 | 1. User is able to log in successfully. 2. The user should be taken to the 'Account page and the User should see the correct account details. 3. The user should be able to see the correct transaction history. | 1. User is able to log in successfully. 2. The user should be taken to the 'Account page and the User should see the correct account details. 3. The user should be able to see the correct transaction history. | P1 | PASS
TC_AC_004 | (TS_004) Accounts | Verify that the user can view and download their account statements. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Accounts from the navigation bar. 3. Tap on Account Summary from the left navigation bar. 4. Check the available balance for the account on Total Available Balance. 5. Tap on the forward arrow beside Total Available Balance. 6. Verify that the Correct account number with the correct details is getting displayed. 7. Tap on "View" from right corner. 8. Tap on "Print This page" in the top right corner on View/ Download Account Statement. | Customer ID - 128654925 Password - 12345 | 1. User is able to log in successfully. 2. The user should be taken to the 'Account page and the User should see the correct account details. 3. The user should able to see the correct transaction history is being displayed. 4. The user should be able to print the account statement. | 1. User is able to log in successfully. 2. The user should be taken to the 'Account page and the User should see the correct account details. 3. The user should able to see the correct transaction history is being displayed. 4. The user should be able to print the account statement. | P1 | PASS
TC_AC_005 | (TS_004) Accounts | Verify that the user can set up and manage alerts for their account. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Accounts from the navigation bar. 3. Tap on "Profile Details" in the top right corner. 4. Verify the contact details of a user. 5. Verify the correct email ID and mobile is set up to receive updates related account. | Customer ID - 128654925 Password - 12345 | 1. After login the user navigates to "Profile Details" in the top right corner. 2 The user is able to see the correct contact details. 3. The user can set up and manage alerts for their account on both mobile number and email ID. | 1. After login the user navigates to "Profile Details" in the top right corner. 2 The user is able to see the correct contact details. 3. The user can set up and manage alerts for their account on a mobile number. 4. The user is not able to set up and manage alerts for their account on email ID, | P1 | FAIL | OPEN Banking-BUG-3 (The user is not able to set up and manage alerts for their account on aemail ID,)
TC_AC_006 | (TS_004) Accounts | Verify that the user can update their personal information, such as their contact details and PAN number. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Accounts from the navigation bar. 3. Tap on "Profile Details" in the top right corner. 4. Verify the contact details of a user. 5. Verify that the user can update their personal information, such as their contact details and PAN number. | Customer ID - 128654925 Password - 12345 | 1. Login to the website using valid credentials 2. Tap on Accounts from the navigation bar. 3. Tap on "Profile Details" in the top right corner. 4. Verify the contact details of a user. 5. Verify that the user can update their personal information, such as their contact details and PAN number. | 1. After login the user navigates to "Profile Details" in the top right corner. 2 The user is able to see the correct contact details. 3. The user can update the PAN number 4. The user is not able to update an email ID on their account. | P1 | Blocked | OPEN Banking-BUG-3 (The user is not able to set up and manage alerts for their account on aemail ID,)
TC_AC_007 | (TS_004) Accounts | Verify that the user can update their address. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Accounts from the navigation bar. 3. Tap on "Profile Details" in the top right corner. 4. Verify the contact details of a user. 5. Verify that the user can update their address. | Customer ID - 128654925 Password - 12345 | 1. Login to the website using valid credentials 2. Tap on Accounts from the navigation bar. 3. Tap on "Profile Details" in the top right corner. 4. Verify the contact details of a user. 5. Verify that the user can update their address. | 1. After login the user navigates to "Profile Details" in the top right corner. 2 The user is able to see the correct contact details. 3. The user is able to update their address. | P1 | PASS
TC_AC_008 | (TS_004) Accounts | Verify if the bank website account page is loaded with proper information. | 1. Open the Website URL (https://netbanking.hdfcbank.com/netbanking/) in any supported Browser | 1. Login to the website using valid credentials 2. Tap on Accounts from the navigation bar. 3. Tap on Account Summary from the left navigation bar. 4. Check the available balance for the account on Total Available Balance. 5. Tap on the forward arrow beside Total Available Balance. 6. Verify that the Correct account number with the correct details is getting displayed. 7. Verify all the images are loading properly. 8. Verify all the links loading and navigate to the correct page. | Customer ID - 128654925 Password - 12345 | 1. User is able to log in successfully. 2. The user should be taken to the 'Account page and the User should see the correct account details. 3. The user should be able to see the correct transaction history. 4. All the images and links are loading properly. | 1. User is able to log in successfully. 2. The user should be taken to the 'Account page and the User should see the correct account details. 3. The user should be able to see the correct transaction history. 4. All the images and links are loading properly. | P1 | PASS

## Fund Transfer
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_FT_001 | (TS_005) Fund Transfer | Verify that the fund transfer page is accessible to the user. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. | Customer ID - 128654925 Password - 12345 | The fund transfer page is accessible to the user. | The fund transfer page is accessible to the user. | P1 | PASS
TC_FT_002 | (TS_005) Fund Transfer | Verify that the user can transfer funds between their accounts. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. 5. Enter all necessary account details in the required fields. 6. Enter the total amount to transfer between accounts. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. | P1 | PASS
TC_FT_003 | (TS_005) Fund Transfer | Verify that the user can add beneficiary their account. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. 5. Tap on "Add on Beneficiary" 6. Enter all necessary account details in the required fields. 6. Tap on "Confirm" to add a beneficiary. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can add the beneficiary. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can add the beneficiary. | P1 | PASS
TC_FT_004 | (TS_005) Fund Transfer | Verify that the user can transfer funds to a beneficiary they have added to their account. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Tap on confirm to transfer funds. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. | P1 | PASS
TC_FT_005 | (TS_005) Fund Transfer | Verify if multiple payment options are not getting selected. Only one at a time. | 1. Open the Website URL 2. User is logged in 3. The user have more than one payment option. |  | Customer ID - 128654925 Password - 12345 | Insufficient Data | Test steps are missing. | P1 | Not Tested | Test steps are missing.
TC_FT_006 | (TS_005) Fund Transfer | Verify if the user has access to the online money transfer feature. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. 5. Verify all the money transfer feature is accessible or not. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. The user is able to explore the type of fund transfer option. | 1. The fund transfer page is accessible to the user. 2. The user is able to explore the type of fund transfer option. | P1 | PASS
TC_FT_007 | (TS_005) Fund Transfer | Check if the user can transfer funds option is available during the specific period (7 am to 7 pm RBI working days). | 1. Open the Website URL 2. User is logged in 3. The user is transferring money during the (7 am to 7 pm RBI working days). | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. (NEFT) 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Tap on confirm to transfer funds. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. | P1 | PASS
TC_FT_008 | (TS_005) Fund Transfer | Check if the fund transfer option shows notice for off-business hours transactions. (after 7 am to 7 pm or RBI non-working days). | 1. Open the Website URL 2. User is logged in 3. The user is transferring money during the (7 am to 7 pm RBI working days). | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. (NEFT) 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Tap on confirm to transfer funds. 9. Verify redirected to 2-step-authentication and tap on "Confirm" 10. verify the user is an alert message for off-business hours. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the alert message for off-business hours is displayed on the screen. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the alert message for off-business hours is displayed on the screen. | P1 | PASS
TC_FT_009 | (TS_005) Fund Transfer | Verify if the user can add the beneficiary. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Tap on confirm to transfer funds. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. | P1 | PASS
TC_FT_010 | (TS_005) Fund Transfer | Verify if the fund transfer option allows NEFT or RTGS option for nationalized money transfers. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Verify that all fund transfer options are getting displayed on the fund transfer page. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. The user is able to explore the type of fund transfer option. 3. e.g. NEFT or RTGS, "Transfer within the bank option" or "Transfer other banks" | 1. The fund transfer page is accessible to the user. 2. The user is able to explore the type of fund transfer option. 3. e.g. NEFT or RTGS, "Transfer within the bank option" or "Transfer other banks" | P1 | PASS
TC_FT_011 | (TS_005) Fund Transfer | Verify if the fund transfer page asks for the beneficiary name, IFSC code, bank name, fund amount, and purpose of the transfer. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. 5. Tap on "Add on Beneficiary" 6. Enter all necessary account details in the required fields. e.g. 6. Tap on "Confirm" to add a beneficiary. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, e.g. name, IFSC code, bank name, fund amount, and purpose of the transfer 3. the user can add the beneficiary. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, e.g. name, IFSC code, bank name, fund amount, and purpose of the transfer 3. the user can add the beneficiary. | P1 | PASS
TC_FT_012 | (TS_005) Fund Transfer | Check if the fund transfer page has a 2-step authentication before you finalize the transfer. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. (NEFT) 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Tap on confirm to transfer funds. 9. Verify redirected to 2-step authentication and tap on "Confirm" to finalize the transfer. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. 3. The user can verify 2-step-authentication and tap on "Confirm" to finalize the transfer. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. 3. The user can verify 2-step-authentication and tap on "Confirm" to finalize the transfer. | P1 | PASS
TC_FT_013 | (TS_005) Fund Transfer | Check if the interbank fund transfer happens instantly or not. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. 5. Enter all necessary account details in the required fields. 6. Enter the total amount to transfer between accounts. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. | P1 | PASS
TC_FT_014 | (TS_005) Fund Transfer | Check the amount of time it takes for the funds to be transferred between in-business hours. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer other bank" as the user needs. (NEFT) 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Tap on confirm to transfer funds. 9. Verify redirected to 2-step authentication and tap on "Confirm" to finalize the transfer. 10. The amount of time takes for a fund transfer is less than 3 minutes. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. 3. The amount of time takes for fund transfer is more than 4 minutes. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. 3. The amount of time takes for fund transfer is more than 4 min 23 sec. | P1 | FAIL | OPEN Banking-BUG-4 (The amount of time takes for fund transfer to other bank is more than 4 min 23 sec.)
TC_FT_015 | (TS_005) Fund Transfer | Verify if the amount transferred notification is sent to the sender and receiver. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer other bank" as the user needs. (NEFT) 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Tap on confirm to transfer funds. 9. Verify redirected to 2-step authentication and tap on "Confirm" to finalize the transfer. 10. Verify the amount transferred notification is sent to the sender and receiver. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. 3. The amount transferred notification is sent to the sender and receiver. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. 3. The amount transferred notification is sent to the sender and receiver. | P1 | FAIL | OPEN Banking-BUG-4 (The amount of time takes for fund transfer to other bank is more than 4 min 23 sec.)
TC_FT_016 | (TS_005) Fund Transfer | Check if the amount gets transferred to the exact person mentioned in the beneficiary. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. (NEFT) 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Tap on confirm to transfer funds. 9. Verify redirected to 2-step authentication and tap on "Confirm" to finalize the transfer. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. 3. The amount gets transferred to the exact person mentioned in the beneficiary. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. 3. The amount gets transferred to the exact person mentioned in the beneficiary. | P1 | Blocked | OPEN Banking-BUG-4 (The amount of time takes for fund transfer to other bank is more than 4 min 23 sec.)
TC_FT_017 | (TS_005) Fund Transfer | Verify if the user gets a confirmation message or mail if the payment is successful. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. (NEFT) 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Tap on confirm to transfer funds. 9. Verify if the user gets a confirmation message or mail if the payment is successful. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. 3. The user gets a confirmation message or mail if the payment is successful. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. 3. The user gets a confirmation message or mail if the payment is successful. | P1 | PASS
TC_FT_018 | (TS_005) Fund Transfer | Verify if a pop-up appears if the session has expired. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. (NEFT) 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Take more than x minute to enter all the mandatory details. 8. Tap on confirm to transfer funds. 9. Verify if a pop-up appears if the session has expired. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, takes more than x minute. 3. The user gets a pop-up appears if the session has expired. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, takes more than x minute. 3. The user gets a pop-up that appears if the session has expired. | P1 | PASS
TC_FT_019 | (TS_005) Fund Transfer | Verify if the user is directed back to the application after a successful transaction. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer other bank" as the user needs. (NEFT) 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Tap on confirm to transfer funds. 9. Verify redirected to 2-step authentication and tap on "Confirm" to finalize the transfer. 10. Verify if the user is directed back to the application after a successful transaction. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. 3. The user is directed back to the application after a successful transaction. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, the user can transfer the funds. 3. The user is directed back to the application after a successful transaction. | P1 | PASS

## Cards
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_CD_001 | (TS_006) Cards | Verify that the Cards page is accessible to the user. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Cards from the navigation bar. 3. Verify that the Cards page is accessible to the user. | Customer ID - 128654925 Password - 12345 | The cards page is accessible to the user. | The cards page is accessible to the user. | P1 | PASS
TC_CD_002 | (TS_006) Cards | Verify that the user can block their debit card if it is lost or stolen. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Cards from the navigation bar. 3. Verify that the Cards page is accessible to the user. | Customer ID - 128654925 Password - 12345 | The cards page is accessible to the user. User is should be able to block the debit card. | The cards page is accessible to the user. The user is should be able to block the debit card. | P1 | PASS
TC_CD_003 | (TS_006) Cards | Verify that the user can request a new debit card through the net banking application. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Cards from the navigation bar. 3. Verify that the Cards page is accessible to the user. 4. Tap on request to apply for a new debit card. 5. Enter all the mandatory details. 6. Tap on "Confirm" for successful application. | Customer ID - 128654925 Password - 12345 | The cards page is accessible to the user. The user is able to request for new debit card. | The cards page is accessible to the user. The user is able to request for new debit card. | P1 | PASS
TC_CD_004 | TC_CD_006 | Verify that the system should allow a user to successfully make a payment with a valid debit card. | 1. Open the Website URL 2. User is logged in | 1. Tap on Cards from the navigation bar. 2. Verify that the Cards page is accessible to the user. 3. Check if all the labels and boxes are visible. 4. Verify the payment gateway company logo or name. 5. Check if the debit card number is masked or not. 6. Verify that all the payment options are visible. 7. Check if the color scheme matches the specifications. 8. Enter all mandatory fields. 9. Verify that the user is able to make a successful payment with a valid debit card. | Customer ID - 128654925 Password - 12345 | 1. The Cards page is accessible to the 2. Enter all mandatory fields. 3. The user is able to make a successful payment with a valid debit card. | 1. The Cards page is accessible to the 2. Enter all mandatory fields. 3. The user is able to make a successful payment with a valid debit card. | P1 | PASS
TC_CD_005 | TC_CD_006 | Verify that the page does not proceed to the payment page before all the mandatory information is filled. | 1. Open the Website URL 2. User is logged in | 1. Tap on Cards from the navigation bar. 2. Verify that the Cards page is accessible to the user. 3. Check if all the labels and boxes are visible. 4. Verify the payment gateway company logo or name. 5. Check if the debit card number is masked or not. 6. Verify that all the payment options are visible. 7. Check if the color scheme matches the specifications. 8. Fill in all mandatory fields except the VCC number. 9. Verify that the page does not proceed to the payment page before all the mandatory information is filled. | Customer ID - 128654925 Password - 12345 | 1. The Cards page is accessible to the 2. Enter all mandatory fields. 3. The page does not proceed to the payment page before all the mandatory information is filled. | 1. The Cards page is accessible to the 2. Enter all mandatory fields. 3. The page does not proceed to the payment page before all the mandatory information is filled. | P1 | PASS
TC_CD_006 | TC_CD_006 | Check if the payment is not getting processed with an expired/blocked card. | 1. Open the Website URL 2. User is logged in 3. The user should have expired/blocked card. | 1. Tap on Cards from the navigation bar. 2. Verify that the Cards page is accessible to the user. 3. Check if all the labels and boxes are visible. 4. Verify the payment gateway company logo or name. 5. Select expired/ blocked card. 6. Check if the debit card number is masked or not. 7. Verify that all the payment options are visible. 8. Check if the color scheme matches the specifications. 9. Fill in all mandatory fields. 10. Verify that the payment is not getting processed with an expired/blocked card. | Customer ID - 128654925 Password - 12345 | 1. The Cards page is accessible to the 2. Enter all mandatory fields. 3. The user is unable to complete the payment process. | 1. The Cards page is accessible to the 2. Enter all mandatory fields. 3. The user is unable to complete the payment process. | P1 | PASS
TC_CD_007 | TC_CD_006 | Verify that the page does not proceed to the payment page when the user enters the wrong CVV. | 1. Open the Website URL 2. User is logged in | 1. Tap on Cards from the navigation bar. 2. Verify that the Cards page is accessible to the user. 3. Check if all the labels and boxes are visible. 4. Verify the payment gateway company logo or name. 5. Check if the debit card number is masked or not. 6. Verify that all the payment options are visible. 7. Check if the color scheme matches the specifications. 8. Fill in all mandatory fields correctly except the VCC number. 9. Verify that the page does not proceed to the payment page before all the mandatory information is filled. 10. Repeat steps 1 to 8 with the below combination. and observe the result. - a) Credit/debit card number+wrong date+ right CVV b) Credit/debit card number+ right date+ wrong CVV c) Wrong credit/debit card number+ right date+ right CVV d) And some other similar combinations | Customer ID - 128654925 Password - 12345 | 1. The Cards page is accessible to the 2. Enter all mandatory fields. 3. The page does not proceed to the payment page when the user enters the wrong CVV. | 1. The Cards page is accessible to the 2. Enter all mandatory fields. 3. The page does not proceed to the payment page when the user enters the wrong CVV. | P1 | PASS
TC_CD_008 | TC_CD_006 | Verify if a pop-up appears if the session has expired. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. (NEFT) 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Take more than x minute to enter all the mandatory details. 8. Tap on confirm to transfer funds. 9. Verify if a pop-up appears if the session has expired. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, takes more than x minute. 3. The user gets a pop-up appears if the session has expired. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, takes more than x minute. 3. The user gets a pop-up that appears if the session has expired. | P1 | PASS
TC_CD_009 | TC_CD_006 | Verify that the user gets information about unsuccessful payments. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. (NEFT) 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Take more than x minute to enter all the mandatory details. 8. Tap on confirm to transfer funds. 9. Verify if a pop-up appears if the session has expired. 10. Verify that the user gets information about unsuccessful payments. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, takes more than x minute. 3. The user gets a pop-up appears if the session has expired. 4. The user gets information about unsuccessful payments. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field, takes more than x minute. 3. The user gets information about unsuccessful payments.. | P1 | PASS
TC_CD_010 | TC_CD_006 | Verify if the transaction gets canceled if the wrong OTP is entered. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. (NEFT) 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Take more than x minute to enter all the mandatory details. 8. Tap on confirm to transfer funds. 9. Enter the wrong OTP which was received on the mobile number. 10.Verify if the transaction gets canceled if the wrong OTP is entered. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field. 3. Enter wrong OTP. 4. The transaction gets canceled if the wrong OTP is entered. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field. 3. Enter wrong OTP. 4. The transaction gets canceled if the wrong OTP is entered. | P1 | PASS
TC_CD_011 | TC_CD_006 | Verify if the user gets OTP on the registered mobile number. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Fund Transfer from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. 4. Select "Transfer within the bank option" or "Transfer other bank" as the user needs. (NEFT) 5. Select the already added beneficiary account. 6. Enter all necessary account details in the required fields. 7. Enter the total amount to transfer between accounts. 8. Verify if the user gets OTP on the registered mobile number. 9. Enter the OTP which was received on the mobile number. 10. Tap on confirm to transfer funds successfully. | Customer ID - 128654925 Password - 12345 | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field. 3. The user recievs OTP on the registred mobile number. | 1. The fund transfer page is accessible to the user. 2. Once the user adds the required details in the field. 3. The user recievs OTP on the registred mobile number. | P1 | PASS

## Loans
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_LN_001 | (TS_007) Loans | Verify if the Loans page is accessible to the user. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Loans from the navigation bar. 3. Verify that the fund transfer page is accessible to the user. | Customer ID - 128654925 Password - 12345 | The Loans page is accessible to the user. | The Loans page is accessible to the user. | P1 | PASS
TC_LN_002 | (TS_007) Loans | Verify if all the links are loading and redirecting to the correct pages. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Loans from the navigation bar. 3. Verify that the Loans page is accessible to the user. 4. Verify if all the links are loading and redirecting to the correct pages. | Customer ID - 128654925 Password - 12345 | The Loans page is accessible to the user. All the links are loading and redirecting to the correct pages. | The Loans page is accessible to the user. All the links are loading and redirecting to the correct pages. | P1 | PASS
TC_LN_003 | (TS_007) Loans | Verify if the user is able to apply for loans, with all required documents. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Loans from the navigation bar. 3. Verify that the Loans page is accessible to the user. 4. Enter all the mandatory details. 5. Submit all the mandatory documents. 6. Verify if the user is able to apply for loans, with all required documents. | Customer ID - 128654925 Password - 12345 | The Loans page is accessible to the user. After entering all the mendatory details and submitting documents user is able to apply for loan. | The Loans page is accessible to the user. After entering all the mendatory details and submitting documents user is able to apply for loan. | P1 | PASS
TC_LN_004 | (TS_007) Loans | Verify that the user can view and download loan-related documents, such as loan statements and repayment schedules. | 1. Open the Website URL 2. User is logged in 3. User has already applied for a loan. | 1. Login to the website using valid credentials 2. Tap on Loans from the navigation bar. 3. Verify that the Loans page is accessible to the user. 4. Verify that the user can view. 5. Verify that the user can download loan-related documents, such as loan statements and repayment schedules. | Customer ID - 128654925 Password - 12345 | The Loans page is accessible to the user. The user can view and download loan-related documents, such as loan statements and repayment schedules. | The Loans page is accessible to the user. The user can view and download loan-related documents, such as loan statements and repayment schedules. | P1 | PASS

## Offers
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_OFF_001 | (TS_008) Offers | Verify that the fund transfer page is accessible to the user. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on offers from the navigation bar. 3. Verify that the offers page is accessible to the user. | Customer ID - 128654925 Password - 12345 | The fund offer is accessible to the user. | The fund offer is accessible to the user. | P3 | PASS
TC_OFF_002 | (TS_008) Offers | Verify if all the links are loading and redirecting to the correct pages. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on offers from the navigation bar. 3. Verify that the offers page is accessible to the user. 4. Verify if all the links are loading and redirecting to the correct pages. | Customer ID - 128654925 Password - 12345 | The offers page is accessible to the user. All the links are loading and redirecting to the correct pages. | The offers page is accessible to the user. All the links are loading and redirecting to the correct pages. | P3 | PASS
TC_OFF_003 | (TS_008) Offers | Verify the system’s ability to validate that the customer is eligible for the offer, such as by checking the customer’s purchase history or verifying a promotional code. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on offers from the navigation bar. 3. Verify that the offers page is accessible to the user. 4. Verify if all the links are loading and redirecting to the correct pages. 5. Enter all the details related to the offer. 6. Verify the customer’s purchase history. 7. Enter the correct promotional code to apply the offer. 8. Verify if the offer is getting redeemed successfully. | Customer ID - 128654925 Password - 12345 | The offers page is accessible to the user. The offer is applied successfully by entering all the correct details. | The offers page is accessible to the user. The offer is applied successfully by entering all the correct details. | P3 | PASS
TC_OFF_004 | (TS_008) Offers | Verify the system’s ability to handle expired discounts by disabling the offer or displaying an error message. | 1. Open the Website URL 2. User is logged in 3. Offer is expired already. | 1. Login to the website using valid credentials 2. Tap on offers from the navigation bar. 3. Verify that the offers page is accessible to the user. 4. Verify if all the links are loading and redirecting to the correct pages. 5. Enter all the details related to the offer. 6. Verify the customer’s purchase history. 7. Enter the correct promotional code to apply the offer. 8. Verify the expiry date of the offer. 9. Confirm if users cannot use expired offers. 10. Verify that the offer is grayed out and cannot be selected for application. | Customer ID - 128654925 Password - 12345 | The offers page is accessible to the user. The offer is grayed out and cannot be selected for application. | The offers page is accessible to the user. The offer is grayed out and cannot be selected for application. | P3 | PASS
TC_OFF_005 | (TS_008) Offers | Verify the system’s ability to apply the discount to the customer’s order or purchase. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on offers from the navigation bar. 3. Verify that the offers page is accessible to the user. 4. Verify if all the links are loading and redirecting to the correct pages. 5. Enter all the details related to the offer. 6. Verify the customer’s purchase history. 7. Enter the correct promotional code to apply the offer. 8. Verify if the offer is getting redeemed successfully. 9. Verify the correct discount for the customer’s order or purchase. | Customer ID - 128654925 Password - 12345 | The offers page is accessible to the user. The offer is applied successfully by entering all the correct details. The correct discount for the customer’s order or purchase. | The offers page is accessible to the user. The offer is applied successfully by entering all the correct details. The correct discount for the customer’s order or purchase. | P3 | PASS
TC_OFF_006 | (TS_008) Offers | Verify the system’s ability to handle a limit on the number of times the discount can be used, such as by disabling the offer after a x number of uses. | 1. Open the Website URL 2. User is logged in 3. User must have an offer. 4. Offer can be user only once. | 1. Login to the website using valid credentials 2. Tap on offers from the navigation bar. 3. Verify that the offers page is accessible to the user. 4. Verify if all the links are loading and redirecting to the correct pages. 5. Enter all the details related to the offer. 6. Verify the customer’s purchase history. 7. Enter the correct promotional code to apply the offer. 8. Verify if the offer is getting redeemed successfully. 9. Try to apply the same offer once again. 10. Verify that the user is not able to redeem the same offer twice. | Customer ID - 128654925 Password - 12345 | The offers page is accessible to the user. The offer is applied successfully by entering all the correct details. The user is not able to redeem the same offer twice. | The offers page is accessible to the user. The offer is applied successfully by entering all the correct details. The user is not able to redeem the same offer twice. | P3 | PASS
TC_OFF_007 | (TS_008) Offers | Verify the system’s ability to validate that the customer is eligible for the offer, such as by checking the customer’s purchase history or verifying a promotional code Percent (%) OFF Offer. | 1. Open the Website URL 2. User is logged in 3. Offer Used: Percent (%) OFF Offer. | 1. Login to the website using valid credentials 2. Tap on offers from the navigation bar. 3. Verify that the offers page is accessible to the user. 4. Verify if all the links are loading and redirecting to the correct pages. 5. Enter all the details related to the offer. 6. Verify the customer’s purchase history. 7. Enter the correct promotional code of twenty Percent (20 %) OFF Offer. to apply the offer. 8. Verify if the offer is getting redeemed successfully. | Customer ID - 128654925 Password - 12345 | The offers page is accessible to the user. The twenty Percent (20 %) OFF Offer is applied successfully by entering all the correct details. | The offers page is accessible to the user. The twenty Percent (20 %) OFF Offer is not applied correctly. User is getting 25 % off instead of 20 % | P3 | FAIL | OPEN Banking-BUG-5 (For offer 20% OFF, User is getting 25 % off instead of 20 %)
TC_OFF_008 | (TS_008) Offers | Verify the system’s ability to validate that the customer is eligible for the offer, such as by checking the customer’s purchase history or verifying a promotional code 500 Rs OFF Offer on more 1500 or more purchages. | 1. Open the Website URL 2. User is logged in 3. Offer Used: 500 Rs OFF Offer on more 1500 or more purchage. | 1. Login to the website using valid credentials 2. Tap on offers from the navigation bar. 3. Verify that the offers page is accessible to the user. 4. Verify if all the links are loading and redirecting to the correct pages. 5. Enter all the details related to the offer. 6. Verify the customer’s purchase history. 7. Enter the correct promotional code of 500 Rs OFF Offer on more 1500 or more purchage Offer. to apply the offer. 8. Verify if the offer is getting redeemed successfully. | Customer ID - 128654925 Password - 12345 | The offers page is accessible to the user. The 500 Rs OFF Offer on more 1500 or more purchage offer is applied successfully by entering all the correct details. | The offers page is accessible to the user. The 500 Rs OFF Offer on more 1500 or more purchage Offer is applied successfully by entering all the correct details. | P3 | PASS
TC_OFF_009 | (TS_008) Offers | Verify the system’s ability to validate that the customer is eligible for the offer, such as by checking the customer’s purchase history or verifying a promotional code Buy One Get .other For Rs. 500. | 1. Open the Website URL 2. User is logged in 3. Offer Used: Buy One Get .other For Rs. 500. | 1. Login to the website using valid credentials 2. Tap on offers from the navigation bar. 3. Verify that the offers page is accessible to the user. 4. Verify if all the links are loading and redirecting to the correct pages. 5. Enter all the details related to the offer. 6. Verify the customer’s purchase history. 7. Enter the correct promotional code of Buy One Get .other For Rs. 500 Offer to apply the offer. 8. Verify if the offer is getting redeemed successfully. | Customer ID - 128654925 Password - 12345 | The offers page is accessible to the user. The Buy One Get .other For Rs. 500 offer is applied successfully by entering all the correct details. | The offers page is accessible to the user. The Buy One Get other For Rs. 500 offer is applied successfully by entering all the correct details. | P3 | PASS

## Investment
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_IN_001 | (TS_009) Investment | Verify that the Investment page is accessible to the user. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Investment from the navigation bar. 3. Verify that the Investment page is accessible to the user. | Customer ID - 128654925 Password - 12345 | The Investment page is accessible to the user. | The Investment page is accessible to the user. | P2 | PASS
TC_IN_002 | (TS_009) Investment | Verify if all the links are loading and redirecting to the correct pages. | 1. Open the Website URL 2. User is logged in | 1. Login to the website using valid credentials 2. Tap on Loans from the navigation bar. 3. Verify that the Loans page is accessible to the user. 4. Verify if all the links are loading and redirecting to the correct pages. | Customer ID - 128654925 Password - 12345 | The Investment page is accessible to the user. All the links are loading and redirecting to the correct pages. | The Investment page is accessible to the user. All the links are loading and redirecting to the correct pages. | P2 | PASS
TC_IN_003 | (TS_009) Investment | Verify that users can view and download investment-related documents, such as mutual fund statements. | 1. Open the Website URL 2. User is logged in 3. The user has already an Investment. | 1. Login to the website using valid credentials 2. Tap on Investment. from the navigation bar. 3. Verify that the Investment. page is accessible to the user. 4. Verify that the user can view Investment.. 5. Verify that the user can download Investment.-related documents, such as mutual fund statements and returns. | Customer ID - 128654925 Password - 12345 | The Loans page is accessible to the user. The user can download Investment.-related documents, such as mutual fund statements and returns. | The Loans page is accessible to the user. The user can download Investment.-related documents, such as mutual fund statements and returns. | P2 | PASS